## HODASSA Review
HODASSA ¦ Project Cost Review
Fictional contractor demonstration ¦ GBP excluding VAT ¦ Customer edition • 10 October 2026
Reporting date (edit) |  | 2026-09-30 | Checks › | Costs › | Issues › | Projects ›
DATA CHECKS PASS — review loss and budget warnings below
Contract value | Cost budget | Actual costs | Forecast costs | Forecast profit | Forecast margin
903000 | 721460 | 392500 | 777600 | 125400 | 13.89%
Invalid costs | Unmapped costs | After date (valid) | Project input issues | Loss-making jobs | Over-budget jobs
0 | 0 | 0 | 0 | 1 | 4
Update project and cost tables; enter 0 only when no remaining cost exists. Keep POs and ETC current at the reporting date.
1 loss-making project(s) ¦ 4 over budget ¦ 0 valid later-dated cost record(s) excluded
Charts include available forecasts only. BLOCKED means unavailable, not £0.
Project | Cost budget | Actual costs | Forecast costs | Forecast profit | Margin | Issues / action required
Heathrow AHU Upgrade | 151700 | 72500 | 131000 | 54000 | 29.19% | No issues
Bristol HVAC Retrofit | 71760 | 56300 | 83900 | 8100 | 8.804% | OVER BUDGET
Surrey Process Cooling | 201600 | 88100 | 213100 | 26900 | 11.21% | OVER BUDGET
Reading Boiler Replacement | 60800 | 71900 | 82900 | -6900 | -9.079% | LOSS ¦ OVER BUDGET
Oxford Cleanroom Ventilation | 235600 | 103700 | 266700 | 43300 | 13.97% | OVER BUDGET
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: original Portfolio!B4 cutoff, 30 September 2026. Single reporting-date control for revised calculations. Changing it changes actual-cost eligibility; refresh remaining POs and ETC to the same date.

## HODASSA Projects
| HODASSA ¦ Edit projects | [6 empty] | Back to dashboard | Review project issues
Fictional data • Blue cells are inputs • GBP excluding VAT • Add rows inside the table
Remaining POs only. Unplaced ETC excludes actuals and POs. Blank ≠ zero.
Job ID | Project | Owner | Contract GBP | Budget GBP | Progress | Open POs GBP | Unplaced ETC | HOW TO UPDATE
2601 | Heathrow AHU Upgrade | Demo manager A | 185000 | 151700 | 71% | 18500 | 40000
2602 | Bristol HVAC Retrofit | Demo manager B | 92000 | 71760 | 68% | 9600 | 18000 | 1. Enter one unique job ID per project.
2603 | Surrey Process Cooling | Demo manager A | 240000 | 201600 | 45% | 45000 | 80000 | 2. POs = still-unspent purchase orders only.
2604 | Reading Boiler Replacement | Demo manager C | 76000 | 60800 | 82% | 5000 | 6000 | 3. ETC = work not actual and not ordered.
2605 | Oxford Cleanroom Ventilation | Demo manager B | 310000 | 235600 | 38% | 58000 | 105000 | 4. Blank ETC blocks forecasts; 0 is explicit.
5. Progress is manual; it does not drive costs.
Add a table row with Tab from its last cell.
Do not paste records outside the table.
Inputs-only table: no formulas to overwrite.
Calculations and dashboard outputs are protected.
Keep table headers unchanged; do not delete columns.
Note on G6: Fábio: Remaining purchase order balance only, as of the reporting date. Reduce this balance when the related cost is recognised as an actual; do not include the full original PO.
Note on H6: Fábio: Estimated future costs not yet actual and not already included in remaining purchase orders. Blank means unknown/incomplete. Enter a numeric 0 only if no unplaced work remains.
Note on A7: Fábio: Source: supplied HODASSA fictional contractor demonstration, original Projects!A7:H11. All 5 sample projects copied unchanged; baseline reporting date 30 September 2026.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!B7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!C7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!D7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!E7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!F7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!G7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!H7 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!A8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!B8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!C8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!D8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!E8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!F8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!G8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!H8 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!A9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!B9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!C9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!D9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!E9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!F9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!G9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!H9 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!A10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!B10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!C10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!D10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!E10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!F10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on G10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!G10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!H10 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!A11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!B11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!C11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!D11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!E11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!F11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!G11 ¦ Baseline 30 September 2026 ¦ Editable project input.
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Projects!H11 ¦ Baseline 30 September 2026 ¦ Editable project input.

## HODASSA Costs
| HODASSA ¦ Enter costs |  |  |  |  | Back to dashboard | Review cost issues
Fictional data • Blue cells are inputs • GBP excluding VAT • Add rows inside the table
Use a unique cost ID and listed job ID. Valid later dates are excluded, not invalid.
Cost ID | Date | Job ID | Description | Quantity | Rate GBP | HOW TO ENTER COSTS
C-01 | 2026-08-10 | 2601 | Equipment package | 1 | 40000
C-02 | 2026-09-05 | 2601 | Labour hours | 500 | 35 | 1. Use a unique cost ID, not an invoice total twice.
C-03 | 2026-09-15 | 2601 | Installation subcontract | 1 | 15000 | 2. Select Job ID from the dropdown.
C-11 | 2026-08-10 | 2602 | Equipment package | 1 | 18000 | 3. Quantity > 0; rate ≥ 0; describe the cost.
C-12 | 2026-09-05 | 2602 | Labour hours | 580 | 35 | 4. Valid dates after the cutoff are AFTER DATE.
C-13 | 2026-09-15 | 2602 | Installation subcontract | 1 | 18000 | 5. See Calculations for cost amounts and issues.
C-21 | 2026-08-10 | 2603 | Equipment package | 1 | 44000
C-22 | 2026-09-05 | 2603 | Labour hours | 660 | 35 | Add a table row with Tab from its last cell.
C-23 | 2026-09-15 | 2603 | Installation subcontract | 1 | 21000 | Pasting may bypass validation; audit still checks.
C-31 | 2026-08-10 | 2604 | Equipment package | 1 | 22000
C-32 | 2026-09-05 | 2604 | Labour hours | 740 | 35
C-33 | 2026-09-15 | 2604 | Installation subcontract | 1 | 24000 | Reduce remaining POs after posting their costs.
C-41 | 2026-08-10 | 2605 | Equipment package | 1 | 48000 | Keep table headers unchanged; do not delete columns.
C-42 | 2026-09-05 | 2605 | Labour hours | 820 | 35
C-43 | 2026-09-15 | 2605 | Installation subcontract | 1 | 27000
Note on B6: Fábio: Actuals include valid records dated on or before the one reporting date on HODASSA Review!D4. Valid later dates are AFTER DATE rather than invalid. Incomplete or invalid later-dated records still require review.
Note on C6: Fábio: Select a Job ID from the expandable project register. Missing, unknown or ambiguous IDs prevent reliable allocation and block portfolio forecasts until corrected.
Note on A7: Fábio: Source: supplied HODASSA fictional contractor demonstration, original Cost log!A7:F21. All 15 sample cost records copied unchanged. Costs are quantity × rate, rounded to pence, GBP excluding VAT.
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B7 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C7 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D7 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E7 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F7 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F8 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F9 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F10 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F11 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F12 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F13 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F14 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F15 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F16 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F17 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F18 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F19 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F20 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!A21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!B21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on C21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!C21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!D21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on E21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!E21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.
Note on F21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: supplied fictional HODASSA demo ¦ Original Cost log!F21 ¦ Baseline 30 September 2026 ¦ Editable cost input; GBP excluding VAT.

## HODASSA Calculations
HODASSA ¦ Cost and project calculations | [11 empty] | Core version notes and proposed enhanced version
Protected business logic and validation: cost records at A18; project forecasts at M18.
As of 30 Sep 2026 |  |  | Back to dashboard |  | Edit costs |  | Edit projects |  | Project audit → |  | Version notes → | Original Portfolio, Projects and Cost log tabs are preserved. Revised tabs use only hdProjects, hdCosts and hdReportDate.
Control | Count / status | [10 empty] | Contract value | Cost budget | Actual costs | Forecast costs | Forecast profit | Forecast margin
Invalid cost records | 0 | [10 empty] | 903000 | 721460 | 392500 | 777600 | 125400 | 13.89%
Unmapped / ambiguous project records | 0
Valid costs after reporting date | 0
Projects with input problems | 0
Reporting date valid | TRUE
Accepted actual subtotal (not a complete forecast) | 392500
Overall data status | PASS
[30 empty] | Budget vs forecast cost ¦ GBP |  |  | Forecast profit / loss ¦ GBP
All cost records ↓
Red = invalid; amber = valid after date
Chart sources — validated projects only; unavailable forecasts are excluded
Cost ID | Date | Job ID | Description | Quantity | Rate GBP | Cost GBP | Specific problem(s) | Record status | Project mapping | Accepted GBP | Cost input row | Job ID | Project | Owner | Contract GBP | Budget GBP | Progress | Open POs GBP | Unplaced ETC | Project input problem(s) | Invalid cost rows | Accepted actual subtotal | Actual GBP | Forecast GBP | Profit GBP | Margin | Budget review | Profit review | Data review | Project | Cost budget | Forecast cost | Project | Forecast profit / loss
C-01 | 2026-08-10 | 2601 | Equipment package | 1 | 40000 | 40000 | OK | INCLUDED | MAPPED | 40000 | 7 | 2601 | Heathrow AHU Upgrade | Demo manager A | 185000 | 151700 | 71% | 18500 | 40000 | OK | 0 | 72500 | 72500 | 131000 | 54000 | 29.19% | WITHIN BUDGET | PROFIT | OK | Heathrow AHU Upgrade | 151700 | 131000 | Heathrow AHU Upgrade | 54000
C-02 | 2026-09-05 | 2601 | Labour hours | 500 | 35 | 17500 | OK | INCLUDED | MAPPED | 17500 | 8 | 2602 | Bristol HVAC Retrofit | Demo manager B | 92000 | 71760 | 68% | 9600 | 18000 | OK | 0 | 56300 | 56300 | 83900 | 8100 | 8.804% | OVER BUDGET | PROFIT | OK | Bristol HVAC Retrofit | 71760 | 83900 | Bristol HVAC Retrofit | 8100
C-03 | 2026-09-15 | 2601 | Installation subcontract | 1 | 15000 | 15000 | OK | INCLUDED | MAPPED | 15000 | 9 | 2603 | Surrey Process Cooling | Demo manager A | 240000 | 201600 | 45% | 45000 | 80000 | OK | 0 | 88100 | 88100 | 213100 | 26900 | 11.21% | OVER BUDGET | PROFIT | OK | Surrey Process Cooling | 201600 | 213100 | Surrey Process Cooling | 26900
C-11 | 2026-08-10 | 2602 | Equipment package | 1 | 18000 | 18000 | OK | INCLUDED | MAPPED | 18000 | 10 | 2604 | Reading Boiler Replacement | Demo manager C | 76000 | 60800 | 82% | 5000 | 6000 | OK | 0 | 71900 | 71900 | 82900 | -6900 | -9.079% | OVER BUDGET | LOSS | OK | Reading Boiler Replacement | 60800 | 82900 | Reading Boiler Replacement | -6900
C-12 | 2026-09-05 | 2602 | Labour hours | 580 | 35 | 20300 | OK | INCLUDED | MAPPED | 20300 | 11 | 2605 | Oxford Cleanroom Ventilation | Demo manager B | 310000 | 235600 | 38% | 58000 | 105000 | OK | 0 | 103700 | 103700 | 266700 | 43300 | 13.97% | OVER BUDGET | PROFIT | OK | Oxford Cleanroom Ventilation | 235600 | 266700 | Oxford Cleanroom Ventilation | 43300
C-13 | 2026-09-15 | 2602 | Installation subcontract | 1 | 18000 | 18000 | OK | INCLUDED | MAPPED | 18000 | 12
C-21 | 2026-08-10 | 2603 | Equipment package | 1 | 44000 | 44000 | OK | INCLUDED | MAPPED | 44000 | 13
C-22 | 2026-09-05 | 2603 | Labour hours | 660 | 35 | 23100 | OK | INCLUDED | MAPPED | 23100 | 14
C-23 | 2026-09-15 | 2603 | Installation subcontract | 1 | 21000 | 21000 | OK | INCLUDED | MAPPED | 21000 | 15
C-31 | 2026-08-10 | 2604 | Equipment package | 1 | 22000 | 22000 | OK | INCLUDED | MAPPED | 22000 | 16
C-32 | 2026-09-05 | 2604 | Labour hours | 740 | 35 | 25900 | OK | INCLUDED | MAPPED | 25900 | 17
C-33 | 2026-09-15 | 2604 | Installation subcontract | 1 | 24000 | 24000 | OK | INCLUDED | MAPPED | 24000 | 18
C-41 | 2026-08-10 | 2605 | Equipment package | 1 | 48000 | 48000 | OK | INCLUDED | MAPPED | 48000 | 19
C-42 | 2026-09-05 | 2605 | Labour hours | 820 | 35 | 28700 | OK | INCLUDED | MAPPED | 28700 | 20
C-43 | 2026-09-15 | 2605 | Installation subcontract | 1 | 27000 | 27000 | OK | INCLUDED | MAPPED | 27000 | 21
Formulas:
Count / status = IF(hdCosts[Date]="","",hdCosts[Date])

## HODASSA Checks
HODASSA ¦ Independent model checks
Independent reconciliations only. Business calculations are on HODASSA Calculations.
MODEL STATUS | PASS |  |  |  | Back to dashboard
Failed checks / input review | None
Independent check | Expected / source | Model / output | Difference | Result | Where to fix
Project coverage | 5 | 5 | 0 | PASS | Project inputs and spill formulas
Cost record coverage | 15 | 15 | 0 | PASS | Cost inputs and spill formulas
Reporting-date validity | 1 | 1 | 0 | PASS | Reporting date on dashboard
Accepted costs re-performed | 392500 | 392500 | 0 | PASS | Cost validation and accepted amounts
Project allocation reconciles | 392500 | 392500 | 0 | PASS | Project mapping and accepted cost allocation
Forecast composition | 777600 | 777600 | 0 | PASS | Actual costs + open POs + unplaced ETC
Forecast profit | 125400 | 125400 | 0 | PASS | Contract less forecast cost
Weighted portfolio margin | 13.89% | 13.89% | 0% | PASS | Portfolio profit divided by contract
Dashboard totals match calculations | 0 | 0 | 0 | PASS | Dashboard headline links
Chart source coverage mismatches | 0 | 0 | 0 | PASS | Validated chart source spills
Forecast chart total | 777600 | 777600 | 0 | PASS | Forecast chart source
Profit chart total | 125400 | 125400 | 0 | PASS | Profit chart source

## HODASSA Admin (hidden)
HODASSA ¦ Internal release notes and historical tests
Internal reference only. Historical results below are not the current release verification.
Source: all 5 projects and 15 costs copied unchanged from the supplied fictional demonstration; no external financial data added.
|  |  | Verification scenario | Result | Expected behaviour | Observed | Restored | Run date | Notes | Separate file limitation: this session can edit the open workbook, not Save As or deliver a second file. Save a separate .xlsx copy before distribution.
|  |  | Baseline reconciliation | PASS | £903k / £721,460 / £392,500 / £777,600 / £125,400 / 13.9% | All six target totals reconcile; margin 13.9%. | Yes | 2026-10-10 |  | Protection: inputs-only tables remain unprotected for normal typing and expansion. All calculation outputs are on protected sheets; no password is set.
|  |  | Add project + chart coverage | PASS | Six projects in totals, detail and BOTH charts | Contract £913000; forecast £780600; chart categories 6/6 | Yes | 2026-10-10 |  | Enhanced option A: a separately approved .xlsm version with a VBA UserForm: enter details → validate → append → confirm; PDF export button.
|  |  | Add cost to new project | PASS | Actual +£500; new project forecast £3,500 | Actual £393000; forecast £781100; new project £3500 | Yes | 2026-10-10 |  | Enhanced option B: keep .xlsx and deploy an Office add-in task pane for a genuine form. A workbook alone cannot contain that deployed add-in.
|  |  | Duplicate cost ID | PASS | Both duplicate rows and affected projects blocked | Invalid 2; actual/forecast BLOCKED/BLOCKED; Duplicate cost ID | Yes | 2026-10-10 |  | I can provide the VBA or Office.js implementation and edit the workbook here. I cannot install/run VBA, deploy an add-in, or create a PDF file through these tools.
|  |  | Unknown project ID | PASS | Unmapped warning and every forecast blocked | Unmapped 1; Unknown project ID; portfolio BLOCKED | Yes | 2026-10-10 | Additional wildcard ID test: PASS; forecast withheld. | No macros, persistent scripts, form buttons or export button were installed. Hosting, trust, Excel-platform compatibility and end-to-end export require separate setup/testing.
|  |  | Blank required estimate | PASS | Forecast withheld; actuals remain valid | Unplaced ETC required: enter 0 only if none remains | Yes | 2026-10-10 |  | An invalid record blocks its associated project. Missing/unknown/ambiguous project IDs block every forecast because their allocation is unresolved.
|  |  | Explicit zero estimate | PASS | Zero accepted; forecast £737,600 | Forecast £737600; profit £165400 | Yes | 2026-10-10 |  | Invalid later-dated records still require review. Valid later-dated records are AFTER DATE, excluded from actuals, and not validation errors.
|  |  | Reporting date + future costs | PASS | Future ≠ invalid; cutoffs recalculate actuals | 31 Aug: £172000 / 10 later; 15 Oct includes £500 | Yes | 2026-10-10 | Remaining POs/ETC stay manual; no historical snapshot | Changing the date does not recreate historical POs or ETC. Refresh the remaining-cost inputs to that same reporting date.
|  |  | Incomplete / invalid cost | PASS | Specific reasons; associated forecast blocked | Missing description; Missing or non-numeric rate | Yes | 2026-10-10
|  |  | Restoration + protection | PASS | 5/15 original records; protected formulas; editable tables | Exact original values and types restored; IDs retained as text. | Yes | 2026-10-10 | Output protection verified. Interactive clicks/Save As not automated.
Baseline project inputs — internal restoration snapshot
Job ID | Project | Owner | Contract GBP | Budget GBP | Progress | Open POs GBP | Unplaced ETC
2601 | Heathrow AHU Upgrade | Demo manager A | 185000 | 151700 | 0.71 | 18500 | 40000
2602 | Bristol HVAC Retrofit | Demo manager B | 92000 | 71760 | 0.68 | 9600 | 18000
2603 | Surrey Process Cooling | Demo manager A | 240000 | 201600 | 0.45 | 45000 | 80000
2604 | Reading Boiler Replacement | Demo manager C | 76000 | 60800 | 0.82 | 5000 | 6000
2605 | Oxford Cleanroom Ventilation | Demo manager B | 310000 | 235600 | 0.38 | 58000 | 105000
Baseline cost inputs — internal restoration snapshot
Cost ID | Date | Job ID | Description | Quantity | Rate GBP
C-01 | 46244 | 2601 | Equipment package | 1 | 40000
C-02 | 46270 | 2601 | Labour hours | 500 | 35
C-03 | 46280 | 2601 | Installation subcontract | 1 | 15000
C-11 | 46244 | 2602 | Equipment package | 1 | 18000
C-12 | 46270 | 2602 | Labour hours | 580 | 35
C-13 | 46280 | 2602 | Installation subcontract | 1 | 18000
C-21 | 46244 | 2603 | Equipment package | 1 | 44000
C-22 | 46270 | 2603 | Labour hours | 660 | 35
C-23 | 46280 | 2603 | Installation subcontract | 1 | 21000
C-31 | 46244 | 2604 | Equipment package | 1 | 22000
C-32 | 46270 | 2604 | Labour hours | 740 | 35
C-33 | 46280 | 2604 | Installation subcontract | 1 | 24000
C-41 | 46244 | 2605 | Equipment package | 1 | 48000
C-42 | 46270 | 2605 | Labour hours | 820 | 35
C-43 | 46280 | 2605 | Installation subcontract | 1 | 27000
Baseline reporting date | 2026-09-30
Release 2026-10-10 ¦ Separate-file backup requires user Save As; no backup file created by this session.
No macros or persistent scripts added; retain .xlsx. Website hosting and reopen behaviour require separate verification.
Dependency audit: no retained worksheet formula, workbook/sheet named range or input-validation rule refers to Portfolio, Projects or Cost log. Their charts were confined to obsolete/replaced sheets.
Chart source ranges auto-expand from complete dynamic-array spills (verified with sixth project). Static chart placement may need moving down for portfolios exceeding 17 projects.
Current release tests — 10 October 2026 | Result | Expected | Observed | Restored
Add project and linked £500 cost | PASS | Both charts: new budget £8,000 / forecast £3,500 / profit £6,500 | Native chart series 6/6/6 projects | Yes
Baseline totals | PASS | £903000 / £721460 / £392500 / £777600 / £125400 / 13.887043% | Actual 392500; forecast 777600; profit 125400; invalid 0; unmapped 0; later 0; chart projects 5/5/5; errors 0 | Yes
Blank required ETC | PASS | Project and portfolio forecast BLOCKED; actuals retained; 4 chart projects | Actual 392500; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Explicit zero ETC | PASS | Forecast £737600; profit £165400; first project £91000 | Actual 392500; forecast 737600; profit 165400; invalid 0; unmapped 0; later 0; chart projects 5/5/5; errors 0 | Yes
Duplicate cost ID | PASS | 2 invalid costs; affected project blocked; 4 chart projects | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 2; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Unknown cost project | PASS | Unmapped cost; all forecasts withheld; no real chart projects | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 1; later 0; chart projects 0/0/0; errors 0 | Yes
Wildcard cost project | PASS | Unsafe ID rejected; all forecasts withheld | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 1; later 0; chart projects 0/0/0; errors 0 | Yes
Duplicate project ID | PASS | Ambiguous mapping; all forecasts withheld | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 6; unmapped 6; later 0; chart projects 0/0/0; errors 0 | Yes
Non-numeric rate | PASS | Invalid cost; affected project blocked; 4 chart projects | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Zero quantity | PASS | Invalid cost; affected project blocked | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Missing cost description | PASS | Invalid cost; affected project blocked | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Invalid reporting date | PASS | All actuals and forecasts withheld; no real chart projects | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 0/0/0; errors 0 | Yes
Valid later-dated cost | PASS | 1 AFTER DATE; actual £352500; forecast £737600; no invalid costs | Actual 352500; forecast 737600; profit 165400; invalid 0; unmapped 0; later 1; chart projects 5/5/5; errors 0 | Yes
Invalid later-dated cost | PASS | Negative rate still invalid; affected forecast withheld | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Negative remaining PO | PASS | Project input invalid; forecast withheld | Actual 392500; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Progress above 100% | PASS | Project input invalid; forecast withheld | Actual 392500; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Blank contract | PASS | Contract total and affected forecast withheld | Actual 392500; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Zero contract | PASS | Affected forecast and margin withheld; no division error | Actual 392500; forecast BLOCKED; profit BLOCKED; invalid 0; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Non-date cost entry | PASS | Invalid cost date; affected forecast withheld | Actual BLOCKED; forecast BLOCKED; profit BLOCKED; invalid 1; unmapped 0; later 0; chart projects 4/4/4; errors 0 | Yes
Exact restoration and final workbook audit | PASS | Original 5 projects, 15 costs, text IDs and 30 Sep 2026 date; outputs protected | Exact values/types restored; 12 independent checks PASS; no baseline errors, required blanks or legacy dependencies | Yes
Unavailable charts: invalid projects are filtered out. When all forecasts are blocked, hidden chart-only sources use deliberate #N/A gaps, never £0. Dashboard displays BLOCKED; baseline is error-free.
Final chart state regression | PASS | No zero forecasts; fixed series orientation; expansion and recovery | baseline: PASS; blocked: PASS; recovered: PASS; partial: PASS; newproject: PASS; final: PASS | Yes
New-row validation inheritance | PASS | ETC non-negative; cost project dropdown; Stop alerts retained | Both new table rows inherit validation and Stop alerts; interactive invalid typing not simulated | Yes
Independent check effectiveness | PASS | £1 deliberate forecast mismatch must trigger independent check and dashboard warning | Forecast/profit/margin checks fail; dashboard STOP warning appears; original formula restored | Yes
Website release verification | NOT TESTED | Save/reopen .xlsx; deployment; intended Excel versions | Dashboard is first and active. Separate file backup, Save As, website flow and reopen verification remain manual | Not applicable
Release limitations: backup Save As and saving/reopening the .xlsx are user actions. Website embedding/download flow, older Excel versions and interactive validation alerts were not tested.
No macros, installer, custom forms or exports were added. Forecasts use actuals plus manual remaining POs and ETC; no invoice-to-PO matching or historical estimate snapshots.
Layout: chart sources and detail spill expand automatically. Chart objects have fixed positions; move charts down if the dashboard exceeds 17 projects.